## OVERVIEW
Volume | Out to whom? | Returned? | In EMMSAP? | To-do | Anna's notes
1 Vitry |  | yes | yes
1 Cycles |  | yes | yes
1 Fauvel
2-3 ballades |  |  |  | all | done and awaiting processing.
2-3 rondeaux |  |  |  |  | If Jeremy finishes PMFC 11 I'll ask for help processing them-- he's been working more slowly since the baby
2-3 virelais |  |  |  | all
2-3 motets |  |  |  | (not scanned)
2-3 mass/misc |  |  |  | (not scanned)
PMFC 4 |  | yes | yes
PMFC 5 |  | yes | yes
PMFC 6 | Corwyn Wyatt | mostly | mostly | Giovanni 8, 10-19 | Assigned to Corwyn
PMFC 7 |  | yes | yes
PMFC 8 |  | yes | yes
PMFC 9 | Anna Grau | yes | yes |  | Finish processing
PMFC 10 | Corwyn Wyatt | mostly | mostly | Appendix f not done
PMFC 11 | Jeremy Jennings | to 29 | to 29 | 30-84 | need to process 30-49, Jeremy working on 49-84 now
PMFC 12 |  | twa | yes
PMFC 13 |  | yes | yes |  | #11 Gloria Tenor is incomplete
PMFC 14 |  |  |  | 14-16: Scanned by Solomon
PMFC 15 |  |  |  | Guhl-Muller for EMMSAP
PMFC 16 |  |  |  | but low priority
PMFC 17 |  |  |  | (not scanned)
PMFC 18 |  |  | mostly | Scan and transribe #6 & 30
PMFC 19 |  |  | mostly | Scan and transribe #77, 83, 84, 95
PMFC 20 |  | yes | yes
PMFC 21 |  | yes | mostly | #37 was missing; Wyatt fixing it
PMFC 22 |  | mostly |  | Process
PMFC 23 |  | yes | yes | (120 & 124 intentionally skipped; MSC transcription) | Fixed #14. 63-65 were incomplete in PMFC, but everything from PMFC is included in our files
PMFC 24 | Anna Grau |  | yes | 12-14 -- see the CPDL folder in the EMMSAP folder -- need to be converted and then included
volumes below are beyond the scope of EMMSAP promised to donors but fit within the project definitely…
Marchi Turin | n/a | n/a | YES
OscarV - new transcrip |  |  |  | new discoveries
Marc Lewon Oswald |  |  | YES | Converted
Perz Polish music |  |  |  | (ot scanned) / Poznan 2 done
E15cM 1
E15cM 2 |  |  |  | Early 15th C. Music
E15cM 3 |  |  |  | A lot of overlap with PMFC - so need to go carefully
E15cM 4
E15cM 5
E15cM 6
E15cM 7 | Jennings |  | first section
Turin J.II.9 Mass |  |  |  | (owned as loose leaf by MSC)
Turin J.II.9 Motets
Turin J.II.9 Songs |  |  |  | (low priority -- mostly later music)
Prague 9 | MSC |  |  | Finishing